## Site Master
MIP — SITE MASTER REGISTER · Washington State Manufacturing Portfolio
MIP Platform — Washington State Manufacturing Portfolio · 4 records
Site ID | Site Name | County | State | Acres | Ownership Type | Zoning | Purchase Cost ($M) | Assessed Value ($M) | Parcel ID | Latitude | Longitude | Elevation (ft) | Strategic Tier | Acquisition Status | Current Land Use | Target Use | Dev Timeline (mo) | Total Investment ($M) | Expansion Reserve (ac) | AI Feasibility Score | Engineering Notes
tacoma | Tacoma Industrial Park | Pierce | WA | 320 | Fee Simple | M-2 Heavy Industrial | 88.4 | 104.2 | 0420222-0010 | 47.2529 | -122.4443 | 22 | Tier 1 — Primary | Active Acquisition | Brownfield / Former Industrial | EV + Advanced Manufacturing | 24 | 142 | 180 | 94 | Adjacent to Port of Tacoma. PSE primary feed confirmed. BNSF spur option active. SR-509 grade separation project 2026-2028 — freight impact mitigation plan required.
everett | Everett Aerospace Zone | Snohomish | WA | 480 | Leasehold (Ground Lease) | I-1 Industrial Park | 0 | 218.6 | 00522700400100 | 47.9789 | -122.2021 | 26 | Tier 2 — Secondary | Due Diligence | Active Aerospace / Boeing Supplier | Aerospace + Defense Manufacturing | 36 | 98 | 220 | 82 | Ground lease from Port of Everett. Boeing adjacency creates workforce pipeline. PSE transformer capacity constrained — $18M grid reinforcement required before Phase 1. FEMA AE flood zone on NW parcel — elevation study required.
spokane | Spokane Logistics Corridor | Spokane | WA | 260 | Fee Simple | I-2 General Industrial | 42.6 | 58.8 | 45072.9160 | 47.6588 | -117.426 | 1890 | Tier 2 — Logistics | LOI Executed | Vacant / Former Rail Yard | Regional Distribution + Light Manufacturing | 30 | 124 | 140 | 87 | Former BNSF rail yard — brownfield remediation required ($3.2M). Avista Utilities 115kV corridor adjacency. High solar irradiance — 12 MW ground-mount solar ROI confirmed. Airport cargo connectivity via GEG (4.2 mi).
yakima | Yakima Valley Industrial Campus | Yakima | WA | 190 | Fee Simple | M-1 Light Industrial | 28.1 | 31.4 | 191335-43003 | 46.6021 | -120.5059 | 1066 | Tier 3 — Specialist | Feasibility Study | Vacant Agricultural / Orchard | Net-Zero Solar Manufacturing | 42 | 88 | 90 | 81 | Highest solar irradiance in portfolio (1,820 kWh/m²/yr). Water stress risk — Yakima River basin allocation under WA Dept of Ecology review. Pacific Power 115kV feed available. I-82 access excellent but limited rail (Class 3 shortline only).

## Infrastructure
MIP — INFRASTRUCTURE CAPACITY REGISTER
MIP Platform — Washington State Manufacturing Portfolio · 4 records
Site ID | Power Utility | Grid Voltage (kV) | Available Capacity (MW) | Peak Demand (MW) | Headroom (MW) | Substation Count | Substation Cap (MVA) | Water Source | Water Capacity (MGD) | Water Treatment (MGD) | Water Pressure (PSI) | Gas Provider | Gas Pressure (PSI) | Fiber Provider | Fiber Bandwidth (Gbps) | Backup Power (MW) | Redundancy Rating | Grid Reliability (%) | Dual Feed Available | UPS Capacity (MVA) | Generator Sets | Diesel Storage (gal) | Infrastructure Score | Infra Readiness (%) | CAPEX Required ($M) | Engineering Notes
tacoma | Puget Sound Energy (PSE) | 115 | 82 | 68 | 14 | 2 | 100 | City of Tacoma Water Dept | 12 | 10.8 | 85 | Puget Sound Energy Gas | 60 | Lumen / Comcast Business | 100 | 8.4 | N+1 Partial | 98.2 | No | 6 | 3 | 45000 | 87 | 87 | 12.4 | Primary: PSE 115kV at Industrial Way SW. Secondary 34.5kV distribution via on-site switchyard. Transformer bank T1 (50MVA) and T2 (50MVA). Water: 16-inch main on E 11th St. Dual-feed upgrade budgeted Q3 2026.
everett | Puget Sound Energy (PSE) | 115 | 58 | 54 | 4 | 1 | 60 | City of Everett Water Dept | 9.4 | 8.8 | 72 | Puget Sound Energy Gas | 55 | Lumen / Wave Broadband | 40 | 4.8 | N (Single Feed) | 76.4 | No | 4 | 2 | 28000 | 72 | 72 | 22.8 | CRITICAL: Single-feed 115kV from PSE Everett substation operating at 94% peak capacity. T1 transformer (60MVA) requires replacement. PSE confirmed upgrade timeline Q3 2026 pending board approval. Water: 12-inch main on Everett Mall Way. Gas: 4-inch medium-pressure.
spokane | Avista Utilities | 115 | 71 | 62 | 9 | 2 | 80 | Spokane County Water Dist #3 | 10.2 | 9.4 | 90 | Avista Natural Gas | 65 | Ziply Fiber / Lumen | 100 | 6 | N+1 Full | 99.1 | Yes | 5 | 4 | 36000 | 83 | 83 | 8.6 | Excellent grid position. Avista 115kV dual-feed via Havana substation and Freya substation — full N+1 redundancy. Brownfield remediation adds 4-6 month delay to utility commissioning. Water: 16-inch main on Freya St. Airport proximity adds fiber diversity.
yakima | Pacific Power (PacifiCorp) | 115 | 64 | 56 | 8 | 2 | 70 | City of Yakima Water / Irrigation Dist | 7.2 | 6.8 | 78 | Cascade Natural Gas | 50 | Ziply Fiber | 40 | 5.6 | N (Single Feed) | 97.4 | No | 4 | 2 | 24000 | 74 | 74 | 14.2 | Pacific Power 115kV feed from Naches substation. Single-feed — dual-feed upgrade path identified via Selah substation (4.2mi trench). Water CRITICAL: Basin allocation under WDOE review — closed-loop recycling investment ($4.2M) mandatory before Phase 2. Gas: 4-inch low-pressure — upgrade to 6-inch required.

## Logistics
MIP — LOGISTICS & CONNECTIVITY ASSESSMENT
MIP Platform — Washington State Manufacturing Portfolio · 4 records
Site ID | Nearest Interstate | Interstate Dist (mi) | Nearest Airport | Airport Dist (mi) | Airport Type | Rail Provider | Rail Class | Rail Spurs | Freight Cars/Day | Nearest Port | Port Dist (mi) | Port Type | Truck Docks | Daily Truck Capacity | Labor Pool (30mi) | Workforce Index | Avg Wage ($/hr) | Avg Commute (min) | Logistics Score | Train Runs/Week | Cargo Air Cap (tons/day) | Seasonal Constraint | Notes
tacoma | I-5 | 0.8 | Seattle-Tacoma (SEA) | 12.4 | International Hub | BNSF Railway | Class 1 | 2 | 48 | Port of Tacoma | 1.4 | Container/Bulk | 16 | 420 | 1240000 | 94 | 28.4 | 22 | 94 | 14 | 280 | Minor (SR-509 construction 2026-28) | Excellent multimodal position. BNSF spur at grade with 2 storage tracks (48-car capacity). Port of Tacoma: 2nd largest container port on West Coast — 1.4mi access via Pacific Ave. SEA-TAC: 12.4mi via SR-99/I-5. Workforce: 1.24M labor pool, 28% STEM concentration.
everett | I-5 | 0.4 | Paine Field (PAE) | 0.8 | Commercial/Cargo | BNSF Railway | Class 1 | 1 | 22 | Port of Everett | 1.9 | Industrial/Marina | 10 | 280 | 920000 | 78 | 26.8 | 28 | 82 | 7 | 145 | None | Exceptional aerospace corridor. Paine Field: Boeing 787/777X final assembly 0.8mi — cargo-capable runway 16R/34L (9,010ft). BNSF single spur with 22 car/day capacity. Port of Everett: bulk/breakbulk, heavy lift capable. I-5 on-ramp 0.4mi via 41st St interchange. Workforce strong but aerospace-concentrated.
spokane | I-90 | 0.6 | Spokane International (GEG) | 4.2 | International Cargo | BNSF + Union Pacific | Class 1 | 3 | 64 | Inland Port of Spokane | 2.1 | Intermodal | 24 | 580 | 620000 | 88 | 22.6 | 18 | 92 | 21 | 420 | Wildfire smoke Jun-Sep | BNSF + UP dual-Class-1 — highest rail frequency in portfolio (3 spurs, 64 cars/day). Spokane Intermodal Facility 2.1mi: connects to BNSF Transcontinental and UP overland route. GEG: Amazon Air hub, FedEx cargo sort. I-90 crossroads position serves Pacific NW and Mountain West. Lower labor cost vs Puget Sound ($22.6/hr avg).
yakima | I-82 | 1.1 | Yakima Air Terminal (YKM) | 3.8 | Regional | BNSF Railway (Class 3 Shortline) | Class 3 | 1 | 8 | Port of Kennewick | 58 | River Barge | 8 | 180 | 220000 | 68 | 19.4 | 24 | 72 | 3 | 22 | Irrigation season May-Oct (road weight limits) | Weakest logistics in portfolio. BNSF shortline only (1 run/day, 8 car max). YKM: regional airport, no regular cargo service. I-82 excellent for truck but limited rail redundancy. Port of Kennewick 58mi (Tri-Cities area). Best suited for manufactured goods not requiring just-in-time components. Labor pool limited — recruitment radius must extend to Ellensburg/Tri-Cities.

## Environmental
MIP — ENVIRONMENTAL ASSESSMENT REGISTER
MIP Platform — Washington State Manufacturing Portfolio · 4 records
Site ID | FEMA Flood Zone | 100yr Flood Risk (%) | Seismic Zone | Wetlands (ac) | Protected Species Risk | Annual Irradiance (kWh/m²/yr) | Wind Speed Avg (mph) | Wind Direction | Annual Rainfall (in) | Groundwater Depth (ft) | Soil Type | Soil Bearing (psf) | Environmental Study Status | ESG Score | Carbon Offset (tCO2/yr) | Remediation Required | Remediation Cost ($M) | Air Quality Index | Noise Zone (dB) | Wildlife Buffer (ft) | Tree Canopy (%) | Solar Panel ROI (yr) | Environmental Risk Rating | Permit Complexity | Notes
tacoma | Zone X (Minimal Hazard) | 8 | 2 | 0.8 | Low | 1240 | 8.4 | SW | 38 | 18 | Gravelly Sandy Loam | 3200 | Phase II Complete | 91 | 9200 | Partial (ACM in 2 structures) | 1.8 | 42 | 68 | 200 | 28 | 5.1 | Low | Medium | FEMA Zone X — above 500-yr flood plain. Seismic Zone 2B (moderate PNW). 0.8ac wetland mitigation required (Pierce County). ACM (asbestos) confirmed in 2 legacy structures — abatement scoped at $1.8M. Carbon offset via 2.8MW solar canopy: 9,200 tCO2/yr. Air quality: Tacoma Smelter Plume SEPA review complete — no additional remediation. Storm drainage to Commencement Bay — NPDES permit required.
everett | Zone AE (1% Annual Chance) | 32 | 2 | 3.2 | Medium | 980 | 11.2 | NW | 52 | 8 | Silty Clay / Glacial Till | 2800 | Phase II In Progress | 74 | 4400 | Yes (Petroleum + Lead) | 4.6 | 38 | 74 | 400 | 14 | 8.2 | High | High | CRITICAL: FEMA Zone AE — 100-yr floodplain on NW 8.4ac. Elevation certificate required. Foundation elevation +3.2ft above BFE. Silty clay soil: poor bearing — deep foundation (auger-cast piles) required for Production buildings. Petroleum + Lead contamination from historical Boeing operations. Phase II ESA in progress. Wetlands: 3.2ac Type F stream buffer required per CAO. Wind turbine potential strong (11.2mph avg, NW prevailing).
spokane | Zone X (Unshaded) | 4 | 1 | 0.4 | Low | 1560 | 6.8 | W | 18 | 42 | Sandy Gravel / Basalt | 4800 | Phase I Complete | 83 | 14400 | Minor (Diesel/Oil) | 3.2 | 28 | 58 | 100 | 32 | 3.8 | Low | Low | Best environmental profile. Zone X — minimal flood exposure. Seismic Zone 1 (lowest risk in WA portfolio). Shallow groundwater (42ft) — no dewatering required. Basalt substrate provides excellent foundation bearing (4,800 psf). Former rail yard: diesel/oil contamination scoped at $3.2M — Phase II confirms no LUST issue. 12 MW solar ground-mount confirmed via Spokane County DCD pre-application. Carbon offset 14,400 tCO2/yr at full solar buildout.
yakima | Zone X (Unshaded) | 6 | 1 | 0.2 | Low | 1820 | 5.6 | NW | 8 | 62 | Sandy Loam / Alluvial | 3600 | Phase I Complete | 78 | 18800 | None | 0 | 22 | 52 | 150 | 12 | 2.9 | Low | Low | Highest solar irradiance in enterprise portfolio (1,820 kWh/m²/yr) — net-zero manufacturing achievable by 2028. Zone X, Seismic Zone 1 — lowest combined physical risk. WATER CRITICAL: Yakima River basin 5A water right application under WDOE review — 2.4 MGD surface water right contested. Must secure groundwater right (62ft depth, 120 GPM confirmed yield) as backup. No remediation. Alluvial soil: excellent drainage, standard spread footings adequate. 18,800 tCO2/yr offset at 18MW solar.

## CAD Objects
MIP — INFRASTRUCTURE OBJECT REGISTER (CAD INVENTORY)
MIP Platform — Washington State Manufacturing Portfolio · 26 records
Object ID | Site ID | CAD Layer | Object Type | Label | Area (sqft) | Footprint (ft) | Height (ft) | Phase | CAPEX ($M) | Utility Dependency | Status | Fire Rating (hr) | Occupancy Type | Clear Height (ft) | Crane Capacity (ton) | Loading Docks | Power Draw (kW) | Water Draw (GPM) | Notes
TAC-001 | tacoma | A-BLDG-PROD | Assembly Building | Assembly Block A | 180000 | 450 x 400 | 42 | Phase 1 | 22 | MV Switchgear / 4.16kV | Approved — Design Dev | 2 | F-3 Manufacturing | 38 | 50 | 0 | 4200 | 180 | Tilt-up concrete, 42ft clear height. 50-ton overhead crane runway (2 bays). 12-dock deep-well loading on south elevation. Sprinklered per NFPA-13. EV assembly line floor load: 500 psf.
TAC-002 | tacoma | A-BLDG-PROD | Assembly Building | Assembly Block B | 120000 | 375 x 320 | 36 | Phase 2 | 18 | MV Switchgear / 4.16kV | Concept Design | 2 | F-3 Manufacturing | 32 | 30 | 0 | 3200 | 140 | Tilt-up concrete. 30-ton crane. Battery module assembly — Class I Div 2 electrical in NW quadrant. Drainage trench system for electrolyte containment.
TAC-003 | tacoma | A-BLDG-PROD | Integration Hall | Final Assembly Hall | 80000 | 320 x 250 | 48 | Phase 2 | 14 | MV Switchgear | Concept Design | 2 | F-3 Manufacturing | 44 | 75 | 0 | 2800 | 95 | Steel frame. 75-ton overhead crane for large module lift. Column-free 250ft clear span. Adjacent to rail spur TAC-L01 for direct inbound. Fire suppression: ESFR.
TAC-004 | tacoma | E-UTIL-POWR | Main Substation | Main Substation (34.5kV) | 8500 | 85 x 100 | 18 | Phase 1 | 4.1 | PSE 115kV Grid Feed | Permit Submitted | 3 | U Utility | 18 | 0 | 0 | 0 | 0 | 34.5kV switchyard. T1+T2 50MVA transformers. Control building: 2,400sqft. Security fence perimeter. PSE interconnection agreement executed. SEPA review in progress.
TAC-005 | tacoma | E-UTIL-POWR | Transformer Bank | Transformer Bank (4.16kV) | 1200 | 40 x 30 | 14 | Phase 1 | 1.8 | Main Substation | Design Complete | 3 | U Utility | 14 | 0 | 0 | 0 | 0 | 2x 30MVA step-down transformers. Oil-filled — containment berm required. Adjacent to MV switchgear room. Arc flash study completed.
TAC-006 | tacoma | P-UTIL-WATR | Water Treatment | Water Treatment Facility | 12000 | 150 x 80 | 24 | Phase 1 | 2.1 | City of Tacoma 16-inch Main | Design Development | 2 | U Utility | 24 | 0 | 0 | 120 | 450 | RO + carbon filtration + softening. Process water 450 GPM. Fire suppression reserve: 100,000 gal tank. Dual-pump redundancy. NPDES industrial wastewater permit required.
TAC-007 | tacoma | C-SITE-STRM | Stormwater Facility | Stormwater Retention Basin | 104544 | 240 x 435 (2.4ac) | 12 | Phase 1 | 3.2 | Natural Drainage | Permit Submitted | 0 | U Utility | 0 | 0 | 0 | 0 | 0 | 2.4ac wet detention pond. Water quality treatment per Pierce County SWDM. Bioswale inlet 400LF. Vegetated buffer per CAO. Connected to Commencement Bay via permitted outfall.
TAC-008 | tacoma | A-BLDG-LOGI | Truck Dock Complex | Truck Dock + Staging | 45000 | 375 x 120 | 28 | Phase 2 | 3.4 | Site Roads | Concept Design | 2 | S-1 Storage | 22 | 0 | 16 | 800 | 45 | 16-door dock high, 9-door grade level. 120ft truck court depth. 85 trailer stalls. Weigh station integrated. Operating: 0500-2200 daily, 24hr option Phase 3.
TAC-009 | tacoma | Z-SITE-SOLR | Solar Array | Solar Canopy Array (2.8MW) | 261360 | Parking + Roof | 20 | Phase 3 | 3.8 | Main Substation | Incentive Pending | 0 | U Utility | 20 | 0 | 0 | -2800 | 0 | 2.8MW DC: 6,800 panels (410W bifacial). Parking canopy: 5.2ac. Roof-mount Building A: 1.8ac. Export via net metering (PSE). SEPA categorical exemption. ITC 30% federal tax credit applicable.
TAC-010 | tacoma | A-BLDG-ADMN | Admin / Office | Administration Building | 24000 | 200 x 120 | 32 | Phase 1 | 3.2 | MV Switchgear / Low Voltage | Approved — Design Dev | 1 | B Business | 28 | 0 | 0 | 280 | 40 | 4-story steel frame. 300-person occupancy. LEED Silver target. Curtain wall system. On-site parking 80 stalls. EV charging 40 stalls Phase 1.
TAC-L01 | tacoma | T-RAIL | Rail Spur | BNSF Rail Spur (Track 1) | 0 | 2,400 LF x 14ft | 0 | Phase 1 | 5.6 | BNSF Mainline | BNSF MOA Executed | 0 | Rail Infrastructure | 0 | 0 | 0 | 0 | 0 | 2,400LF standard gauge spur, 286,000 lb car limit. 48-car storage capacity on 2 tracks. Stub-end configuration. Crossing signal at Industrial Way SW. BNSF Memorandum of Agreement executed.
TAC-L02 | tacoma | C-ROAD | Site Road | Primary Haul Road | 0 | 4,800 LF x 40ft | 0 | Phase 1 | 1.4 | Public ROW (SR-509) | Design Development | 0 | Transportation | 0 | 0 | 0 | 0 | 0 | 40ft two-lane haul road, 100,000 lb axle load. Signalized access at Pacific Ave. Secondary access at East 11th St. Truck exclusion zone for Assembly Block A east elevation.
EVT-001 | everett | A-BLDG-PROD | Aerospace Assembly | Primary Aerospace Assembly | 240000 | 600 x 400 | 60 | Phase 1 | 32 | MV Switchgear (Post-Upgrade) | Concept Design | 2 | F-3 Manufacturing | 56 | 100 | 0 | 6200 | 220 | Steel moment frame, 60ft clear height. 100-ton overhead crane — 2 bays, 200ft span. Designed for large aerospace structure assembly. High bay lighting 100fc. Deep foundation required: 60ft auger-cast piles due to silty clay.
EVT-002 | everett | A-BLDG-PROD | Component Shop | Component Manufacturing Shop | 120000 | 400 x 300 | 36 | Phase 2 | 18 | MV Switchgear | Concept Design | 2 | F-3 Manufacturing | 32 | 30 | 0 | 3800 | 160 | Tilt-up. CNC machining bays — vibration isolation pads required. Cleanroom zone 20,000sqft (ISO Class 8). Compressed air: 4 Atlas Copco ZR 250 units.
EVT-003 | everett | E-UTIL-POWR | Grid Reinforcement | PSE Grid Reinforcement Works | 2000 | 40 x 50 | 20 | Phase 1 | 18 | PSE External | Board Approval Required | 3 | U Utility | 20 | 0 | 0 | 0 | 0 | CRITICAL PATH: New 115kV PSE substation or transformer replacement. 3-mile underground 115kV cable from Everett South Substation. $18M capital — must be approved 6 months before Phase 1 groundbreak. PSE timeline: Q3 2026 if approved Q4 2025.
EVT-004 | everett | C-SITE-FLOD | Flood Mitigation | Flood Mitigation Earthworks | 348480 | 8.0ac earthwork | 0 | Phase 1 | 4.8 | FEMA AE Zone | Design Required | 0 | Civil Infrastructure | 0 | 0 | 0 | 0 | 0 | 8.0ac of NW parcel in FEMA AE zone. Elevation fill 3.2ft above BFE. 1,200LF perimeter berm. French drain system. Outfall structure to Port of Everett stormwater system. FEMA LOMA application required. Geotechnical report in progress.
EVT-L01 | everett | T-RAIL | Rail Spur | BNSF Rail Spur | 0 | 1,200 LF x 14ft | 0 | Phase 2 | 3.2 | BNSF Mainline | Preliminary Routing | 0 | Rail Infrastructure | 0 | 0 | 0 | 0 | 0 | 1,200LF connection from BNSF Everett mainline. Route conflicts with Port of Everett lease boundary — right-of-way negotiation required. 22-car storage. Alternative: truck transfer at Everett Rail Yard (2.1mi).
SPK-001 | spokane | A-BLDG-PROD | Distribution Center | Primary Distribution Center | 160000 | 400 x 400 | 36 | Phase 1 | 20 | MV Switchgear | Design Development | 2 | S-1 Storage | 32 | 0 | 32 | 2800 | 120 | Tilt-up concrete. 32-dock positions. Cross-dock configuration. Automated sortation conveyor rough-in. 38ft clear height. 60,000sqft mezzanine for pick/pack. ESFR sprinkler. Brownfield: utility routing must avoid contamination zone (NE 2.4ac).
SPK-002 | spokane | A-BLDG-PROD | Light Manufacturing | Light Manufacturing Campus | 80000 | 320 x 250 | 30 | Phase 2 | 12 | MV Switchgear | Concept Design | 2 | F-3 Manufacturing | 28 | 20 | 0 | 2400 | 80 | Tilt-up. 20-ton bridge crane. Flexible bay layout — 40ft column grid. Expansion joint designed for Phase 3 addition (80,000sqft). Geothermal HVAC rough-in for future install.
SPK-003 | spokane | Z-SITE-SOLR | Solar Farm | Ground-Mount Solar Farm (12MW) | 2613600 | 60ac solar field | 8 | Phase 1 | 14.4 | Avista 115kV | Permit Submitted | 0 | Renewable Energy | 8 | 0 | 0 | -12000 | 0 | 12MW DC ground-mount. 29,268 panels (410W bifacial). Single-axis tracking. 60ac southeast of site. Export via Avista interconnection (net metering + excess sale). Spokane County permit submitted. BPA transmission headroom confirmed. ITC 30% + Bonus depreciation applicable.
SPK-004 | spokane | C-SITE-BRMF | Brownfield Remediation | Rail Yard Remediation Zone | 104544 | 2.4ac | 0 | Pre-Construction | 3.2 | N/A | Assessment Complete | 0 | Remediation | 0 | 0 | 0 | 0 | 0 | Former BNSF fueling facility. Diesel/oil impacted soil to 14ft depth. 2,400 CY excavation and off-site disposal. Low-temp thermal desorption — confirmatory sampling complete Q2 2026. Does not impact building footprints. Remediation cost included in site acquisition basis.
SPK-L01 | spokane | T-RAIL | Rail Spurs | BNSF + UP Dual Rail Access | 0 | 3 spurs / 4,800 LF total | 0 | Phase 1 | 6.8 | BNSF + Union Pacific | MOA in Negotiation | 0 | Rail Infrastructure | 0 | 0 | 0 | 0 | 0 | 3 spurs: BNSF Transcontinental (Spur 1, 1,800LF), UP Overland (Spur 2, 1,800LF), shared storage (Spur 3, 1,200LF). 64-car/day capacity. Intermodal connection to Spokane Rail Facility 2.1mi. Highest rail capacity in portfolio.
YAK-001 | yakima | A-BLDG-PROD | Manufacturing Hall | Net-Zero Manufacturing Hall | 100000 | 400 x 250 | 32 | Phase 1 | 14 | MV Switchgear / Solar DC Bus | Design Development | 2 | F-3 Manufacturing | 28 | 20 | 0 | 0 | 80 | Designed for net-zero operation: solar DC bus feed, battery storage integrated. High-reflectance roof (SRI > 82). Evaporative pre-cooling for process air. Dry cooling system — zero process water discharge. Floor load 400psf. LED lighting 100fc.
YAK-002 | yakima | Z-SITE-SOLR | Solar Array | Solar Farm + Carport (18MW) | 3484800 | 80ac solar field + 3ac carport | 10 | Phase 1 | 21.6 | Pacific Power 115kV | Design Development | 0 | Renewable Energy | 10 | 0 | 0 | -18000 | 0 | 18MW DC: 43,902 panels (410W bifacial), single-axis tracking. 80ac east field + 3ac carport (staff parking). Battery storage: 8MWh Tesla Megapack. Achieves net-zero by 2028. Pacific Power interconnection application submitted. ITC 30% + Production Tax Credit applicable.
YAK-003 | yakima | P-UTIL-WATR | Water Recycling | Closed-Loop Water Recycling Plant | 8000 | 100 x 80 | 20 | Phase 1 | 4.2 | City of Yakima + Groundwater Well | Design Development | 2 | U Utility | 20 | 0 | 0 | 180 | 0 | MANDATORY: Yakima water stress requires closed-loop system. RO + ultrafiltration + UV disinfection. 95% water recovery. 120 GPM groundwater backup (well permitted at 62ft depth). Zero liquid discharge (ZLD) system. Investment $4.2M — ROI 3.8yr based on avoided water cost.
YAK-L01 | yakima | C-ROAD | Haul Road | I-82 Access Road | 0 | 2,200 LF x 40ft | 0 | Phase 1 | 1.2 | I-82 / SR-24 | Design Development | 0 | Transportation | 0 | 0 | 0 | 0 | 0 | 40ft haul road from I-82 Exit 44. 100,000lb axle load. Truck weight restriction May-Oct (irrigation season road postings). Secondary access via Beaudry Rd. Weight limit compliance monitoring system required.

## Construction Phases
MIP — CONSTRUCTION PHASE PLAN (ALL SITES)
MIP Platform — Washington State Manufacturing Portfolio · 18 records
Site ID | Phase Number | Phase Name | Start Month | Duration (months) | CAPEX ($M) | Buildings / Infrastructure | Utility Requirements | Permit Status | Dependencies | Readiness (%) | Critical Path Item | Notes
tacoma | 1 | Site Preparation & Civil Works | 1 | 4 | 8.2 | TAC-007 (Stormwater), TAC-L01 (Rail Spur), TAC-L02 (Haul Road) | Temporary power 400A/480V | Building Permit + Grading Permit Issued | ACM abatement complete, PSE pre-application accepted | 88 | Stormwater permit (Pierce County) — 12-week lead | Site clearing 320ac. Mass grading 480,000 CY earthwork. Utility trenching (power, water, telecom). Rail spur rough grading. Stormwater basin excavation. Site fence and security.
tacoma | 2 | Utility Infrastructure Installation | 3 | 6 | 18.4 | TAC-004 (Substation), TAC-005 (Transformer), TAC-006 (Water Treatment) | PSE 115kV energisation, City water 16-inch main tap | SEPA + PUD Interconnection + Water System Plan | Phase 1 civil grading complete, PSE interconnection agreement executed | 82 | PSE interconnection approval — 20-week regulatory lead | Main substation construction. Transformer bank installation. 4.16kV distribution duct bank (2,800LF). Water treatment facility. Fire suppression tank (100,000 gal). Telecom and fiber routing.
tacoma | 3 | Production Building Foundations | 5 | 6 | 14.6 | TAC-001 (Assembly A — foundations), TAC-003 (Integration Hall — foundations) | Dewatering system, temporary power from substation | Building Permit + Special Inspection | Substation energised, soil bearing confirmed by geotech | 91 | Crane procurement for 50-ton overhead bridge crane — 20wk lead | Assembly Block A spread footings (500psf). Integration Hall: column footings and grade beams. Underground MEP rough-in. Concrete slab-on-grade 8-inch (6,500psi). Vapor barrier and insulation.
tacoma | 4 | Structural Build — Production Phase | 8 | 10 | 38.8 | TAC-001 (Assembly A complete), TAC-002 (Assembly B begin), TAC-003 (Integration Hall) | Permanent 4.16kV distribution to buildings | Building Permit amendments for crane runway | Phase 3 foundations complete, crane delivered on site | 87 | Tilt-up panel crane logistics — site access critical | Assembly Block A: tilt-up concrete panels, crane runway beams, roof structure, envelope. Integration Hall: steel erection, 75-ton crane install. Assembly Block B foundations begin. MEP rough-in. Dock equipment installation.
tacoma | 5 | Systems Integration & MEP Fit-Out | 14 | 8 | 28.4 | TAC-001 (A complete), TAC-003 (complete), TAC-008 (Truck Dock), TAC-010 (Admin) | Full building power, water, HVAC commissioning | Certificate of Occupancy — TCO Phase 1 | Structural complete, MEP rough-in inspected | 83 | MEP commissioning sequencing — 6-week parallel track | HVAC install and commissioning. Electrical distribution to panels. Fire alarm and suppression final. Assembly Block A production line installation. Admin building fitout. Loading dock equipment. Truck court paving.
tacoma | 6 | Solar + Commissioning + Phase 3 Begin | 18 | 6 | 28 | TAC-009 (Solar Array), TAC-002 (Assembly B complete), Final commissioning | Solar export metering, backup generator commissioning | Building Permit C of O, PSE net metering interconnection | Phase 5 TCO issued, solar incentive applications filed | 72 | Solar ITC application and net metering approval timeline | Solar canopy array installation (2.8MW). Assembly Block B structural completion. All systems commissioning and functional testing. Performance testing 30-day run. Occupancy. Assembly Block B production line installation.
everett | 1 | Flood Mitigation + Grid Reinforcement | 1 | 10 | 24 | EVT-003 (Grid Works), EVT-004 (Flood Earthworks) | PSE construction power, dewatering | FEMA LOMA + PSE Board Approval + Building Permit | PSE $18M approval, FEMA LOMA application, flood study complete | 58 | PSE board approval — external dependency, no internal control | CRITICAL PATH: PSE 115kV reinforcement must begin Month 1. Parallel flood mitigation earthworks on NW 8ac. FEMA LOMA application. Deep foundation study complete. Contamination Phase II complete. Cannot begin production buildings until grid reinforcement confirmed.
everett | 2 | Site Civil + Utility Infrastructure | 8 | 8 | 22.4 | EVT-002 (grid infrastructure), site civil works | PSE energisation post-reinforcement | Grading + Building Permit + PUD Interconnection | PSE reinforcement complete, flood earthworks stable | 72 | Port of Everett ground lease amendment for utility easements | Primary site grading. Utility trenching: 4.16kV duct bank, water main, gas, telecom. New substation installation. Access road construction. Stormwater system. Rail spur preliminary routing.
everett | 3 | Foundation + Structural — Aerospace Assembly | 14 | 12 | 52 | EVT-001 (Primary Aerospace Assembly) | Full building power from reinforced grid | Building Permit (Type I-A, high bay) | Grid energised, deep foundation design complete | 74 | 60ft auger-cast piles for silty clay — 14-week install | 60ft auger-cast piles (estimated 480 piles at 36-inch diameter). Grade beam and foundation slab. Steel erection: 200ft clear span, 60ft clear height. 100-ton crane runway installation. Envelope (metal panel + glazing). MEP rough-in.
everett | 4 | Component Shop + Systems Fitout | 24 | 10 | 28 | EVT-002 (Component Shop), EVT-001 (systems complete) | Cleanroom HVAC, CNC power circuits | Certificate of Occupancy | Assembly Hall structural complete | 68 | Cleanroom validation 8-week independent certification | Component Manufacturing Shop construction. ISO Class 8 cleanroom installation and validation. CNC machining bay vibration isolation. BNSF rail spur negotiations. Admin and support facilities.
spokane | 1 | Brownfield Remediation + Site Prep | 1 | 8 | 8.6 | SPK-004 (Remediation Zone), site civil | Temporary construction power | Ecology Agreed Order + Grading Permit | Phase II ESA complete, WA Ecology cleanup agreement executed | 84 | WA Ecology agreed order execution — regulatory dependency | 2,400 CY contaminated soil excavation and disposal. Confirmatory sampling. Backfill with clean imported fill. Mass grading 260ac. Utility pre-trenching. BNSF + UP MOA negotiation. Site fence and access control.
spokane | 2 | Solar Farm + Utility Infrastructure | 4 | 8 | 24.4 | SPK-003 (Solar Farm 12MW), utility infrastructure | Avista 115kV interconnection, solar export metering | Spokane County CUP + Avista Interconnection Agreement | Remediation confirmatory sampling clean, solar permit approved | 88 | Avista interconnection study — 16-week process | 60ac solar farm construction. Single-axis tracker installation. Avista interconnection and metering. Main substation (12MW capacity). Utility duct bank 3,200LF. Water main connection from Spokane County District #3. Telecom: Ziply Fiber + Lumen diversity.
spokane | 3 | Distribution Center Construction | 8 | 10 | 22.4 | SPK-001 (Distribution Center) | Building power from substation, dock levellers | Building Permit + Certificate of Occupancy | Substation energised, solar farm generating | 82 | Tilt-up panel crane access — coordination with solar installation | Primary distribution center tilt-up construction. 32 dock positions. Automated sortation conveyor rough-in. Cold storage zone 40,000sqft. Fleet parking 200 stalls. ESFR sprinkler. BNSF rail spur Track 1 and Track 2 activation.
spokane | 4 | Light Manufacturing + Rail Integration | 16 | 8 | 18.8 | SPK-002 (Light Manufacturing), rail spurs 2+3 | Additional 4.16kV circuits, compressed air | Building Permit, BNSF/UP final MOA | Phase 3 distribution center operational | 76 | UP rail spur routing approval — external railroad dependency | Light manufacturing campus tilt-up construction. 20-ton bridge crane. Geothermal HVAC rough-in. UP rail spur Track 2 and storage Track 3 installation. Full rail-to-dock intermodal capability.
yakima | 1 | Solar Farm + Water Infrastructure | 1 | 8 | 28.2 | YAK-002 (Solar Farm 18MW), YAK-003 (Water Recycling) | Pacific Power interconnection, groundwater well | Pacific Power Interconnection + WDOE Water Right | WDOE water right application filed, solar permit approved | 74 | WDOE water right — 12-18 month regulatory timeline | 80ac solar farm construction (18MW). Carport solar (3ac). Battery storage: 8MWh Megapack. Closed-loop water recycling plant. Groundwater well (62ft, 120GPM). Pacific Power 115kV interconnection. Net-zero infrastructure foundation.
yakima | 2 | Site Civil + Utility Infrastructure | 6 | 6 | 12.4 | Site civil, utility infrastructure | Solar DC bus, water recycling operational | Grading Permit + Building Permit | Solar generating, water right secured or groundwater confirmed | 78 | I-82 access permit from WSDOT | Mass grading 190ac. I-82 access road construction. Utility duct bank. MV distribution from substation. Compressed air system (dry process). Site drainage (minimal — 8in/yr rainfall, no retention required). Security perimeter.
yakima | 3 | Net-Zero Manufacturing Hall | 10 | 10 | 14 | YAK-001 (Manufacturing Hall) | Solar DC bus, RO water, dry cooling | Building Permit + Certificate of Occupancy | Solar and water infrastructure operational | 82 | Solar DC bus integration commissioning — specialized contractor | Tilt-up concrete manufacturing hall. High-reflectance roof. Evaporative pre-cooling. Solar DC bus integration. Dry cooling system (zero process water). 20-ton bridge crane. Production line installation. Net-zero commissioning and certification.
yakima | 4 | Expansion + Commissioning | 18 | 6 | 8.4 | Expansion Phase 3 preparation, full commissioning | Full export metering, net-zero certification | C of O, ITC 30% application, LEED documentation | Phase 3 production operational, net-zero data baseline established | 68 | LEED certification documentation — 6-month process | Phase 3 expansion pad preparation (90ac reserve). Full commissioning and net-zero performance testing. 30-day energy balance verification. LEED Gold documentation. ITC 30% application. Solar production tax credit application. Workforce training program completion.

## Computed Metrics
MIP — AI FEASIBILITY SCORE COMPUTATION (Weighted Formula)
AI Score = (Infra Readiness × 0.30) + (Logistics × 0.25) + (Workforce × 0.20) + (ESG × 0.15) + (Env Risk Inverse × 0.10)
Site ID | Infra Readiness | Logistics Score | Workforce Index | ESG Score | Env Risk Inverse | AI Feasibility Score (Computed) | Total Investment ($M) | Strategic Tier
tacoma | 87 | 94 | 94 | 91 | 92 | 91.2 | 142 | Tier 1
everett | 72 | 82 | 78 | 74 | 68 | 75.6 | 98 | Tier 2
spokane | 83 | 92 | 88 | 83 | 96 | 87.6 | 124 | Tier 2
yakima | 74 | 72 | 68 | 78 | 94 | 74.9 | 88 | Tier 3